Azalea Park Sequence of Construction & Update

Completed is in Red Current month in Blue Hold in Green

1. Install new fence for dog park (phase 1) – includes demo of one basketball court

Dog Park Complete

1. Culvert in phase 2 area for dog park- Complete
2. Stormwater feature #1 (east end) – includes new creek culvert for sewer access to east

October-100% plans in and reviewed along with project manual. Dan will loop through FSNA

Complete- Determination was made that need for replacement culvert for RWSA was no longer required. Culvert will not be replaced and material order has been cancelled.

1. Pave trail to Azalea Drive and install new bridge/culvert (GRANT)

Will be done this winter after wetlands area construction is out of the way. If asphalt plants are closed will be done next spring

1. Stormwater feature #2 (west side) (GRANT)

Completed

1. Entryway (new sign, landscape, gate) (OLR fund)

New park sign to be ordered once we get NDS to determine “Welcome…” sign design, installation would be same time as park sign. Planting to be done late fall/early winter (starting earlier than November), design pending.

Completed- New gate installed, old gate will be used at Greenbriar Park, new fence/access control installed.

1. Road work (on-street parking and cul-de-sac – east end)

Complete with exception of 30 or so bumper blocks

Access control pending; dirt work to level and protect edges in process.

1. Convert concession into restrooms (GRANT)

Evaluation options in and being assessed.

1. Expand parking lot on west side

Complete

1. Install playground in new location

Had very productive meeting with neighborhood on 10/1 to be finalized 10/22. Probable timeline would have equipment ordered in November. Install function of weather.

1. Demo old playground Won’t be done until new playground is in place
2. Build new basketball courts – demo second old court

Complete, only one court built due to site constraints, goals in by end of October pending weather, possibility of lining this fall pending weather.

1. Install internal paved walkways

Winter and spring work

1. Rotate ball field 180\*

This will likely be FY 14 work, discussion about not rotating due to use.

1. Picnic shelter/concession building

This will likely be FY 14 work

1. Add new amenities (trash cans, etc.)

Will be done/added as necessary or as areas finished out.

1. Added Landscaping (New category)

This is late fall/winter work and will be performed as funding is available and warranted; may be deferred to fall winter of 2013-14 due to heavy over winter construction schedule.

1. Misc

August 2012-Information kiosk by existing front parking will used to post new master plan, contact information and monthly schedule week of 8/6. Original install removed within 24 hours will try again in October.